## Sheet 1
drawing_no | cir_no | joint_no | method | result | complete_date
PS3MP01-40-201-2017-01 | 2016211 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2017-01 | 2016211 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-2019-01 | 2016212 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2019-01 | 2016212 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-2014-01 | 2016210 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2014-01 | 2016210 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-1008-01 | 2016213 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-1008-01 | 2016213 | 4 | MT | ACC | 2018-07-19
PS3MP01-40-201-2011-01 | 2016214 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2011-01 | 2016214 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-2018-01 | 2016215 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2018-01 | 2016215 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-2021-01 | 2016216 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2021-01 | 2016216 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-2023-01 | 2016217 | 1 | MT | ACC | 2018-07-19
PS3MP01-40-201-2023-01 | 2016217 | 2 | MT | ACC | 2018-07-19
PS3MP01-40-201-1008-01 | 2016213 | 1 | MT | ACC | 2018-07-20
PS3MP01-40-201-1008-01 | 2016213 | 3 | MT | ACC | 2018-07-20
PS3MP01-40-201-1005-01 | 2016218 | 3 | MT | ACC | 2018-07-20
PS3MP01-40-201-1005-01 | 2016218 | 6 | MT | ACC | 2018-07-20
PS3MP01-40-201-2016-01 | 2016219 | 1 | MT | ACC | 2018-07-20
PS3MP01-40-201-2016-01 | 2016219 | 2 | MT | ACC | 2018-07-20
PS3MP01-40-201-2005-01 | 2016220 | 65 | UT/MT | ACC | 2018-07-20
PS3MP01-40-201-2006-01 | 2016221 | 23 | UT/MT | ACC | 2018-07-20
PS3MP01-40-201-2006-01 | 2016221 | 24 | UT/MT | ACC | 2018-07-20
PS3MP01-40-201-2007-01 | 2016222 | 38 | UT/MT | ACC | 2018-07-20
PS3MP01-40-201-1003-01 | 2016225 | 1 | MT | ACC | 2018-07-23
PS3MP01-40-201-1003-01 | 2016225 | 3 | MT | ACC | 2018-07-23
PS3MP01-40-201-1003-01 | 2016225 | 5 | UT/MT | ACC | 2018-07-23
PS3MP01-40-201-1003-01 | 2016225 | 7 | MT | ACC | 2018-07-23
PS3MP01-40-201-1007-01 | 2016226 | 2 | MT | ACC | 2018-07-23
PS3MP01-40-201-1007-01 | 2016226 | 5 | MT | ACC | 2018-07-23
PS3MP01-40-201-1010-01 | 2016227 | 1 | MT | ACC | 2018-07-23
PS3MP01-40-201-1010-01 | 2016227 | 3 | MT | ACC | 2018-07-23
PS3MP01-40-201-1010-01 | 2016227 | 5 | MT | ACC | 2018-07-23
PS3MP01-40-201-1010-01 | 2016227 | 7 | UT/MT | ACC | 2018-07-23
PS3MP01-40-201-1011-01 | 2016228 | 1 | MT | ACC | 2018-07-23
PS3MP01-40-201-1011-01 | 2016228 | 2 | MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 1 | MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 2 | MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 3 | UT/MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 4 | MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 7 | MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 8 | MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 9 | UT/MT | ACC | 2018-07-23
PS3MP01-40-201-2013-01 | 2016229 | 10 | MT | ACC | 2018-07-23
PS3MP01-40-201-1005-01 | 2016223 | 2 | MT | ACC | 2018-07-23
PS3MP01-40-201-1005-01 | 2016223 | 5 | MT | ACC | 2018-07-23
PS3MP01-40-201-1007-01 | 2016224 | 3 | MT | ACC | 2018-07-23
PS3MP01-40-201-1007-01 | 2016224 | 6 | MT | ACC | 2018-07-23
PS3MP01-40-201-2007-01 | 2016230 | 37 | UT/MT | ACC | 2018-07-23
PS3MP01-40-201-2026-01 | 2016239 | 1 | MT | ACC | 2018-07-24
PS3MP01-40-201-2026-01 | 2016239 | 2 | MT | ACC | 2018-07-24
PS3MP01-40-201-2026-01 | 2016239 | 3 | MT | ACC | 2018-07-24
PS3MP01-40-201-2026-01 | 2016239 | 4 | MT | ACC | 2018-07-24
PS3MP01-40-201-2028-01 | 2016240 | 1 | MT | ACC | 2018-07-24
PS3MP01-40-201-2028-01 | 2016240 | 2 | MT | ACC | 2018-07-24
PS3MP01-40-201-2028-01 | 2016240 | 3 | MT | ACC | 2018-07-24
PS3MP01-40-201-2028-01 | 2016240 | 4 | MT | ACC | 2018-07-24
PS3MP01-40-201-1003-01 | 2016241 | 2 | MT | ACC | 2018-07-24
PS3MP01-40-201-1003-01 | 2016241 | 4 | MT | ACC | 2018-07-24
PS3MP01-40-201-1003-01 | 2016241 | 6 | UT/MT | ACC | 2018-07-24
PS3MP01-40-201-1003-01 | 2016241 | 8 | MT | ACC | 2018-07-24
PS3MP01-40-201-1005-01 | 2016242 | 1 | MT | ACC | 2018-07-24
PS3MP01-40-201-1005-01 | 2016242 | 4 | MT | ACC | 2018-07-24
PS3MP01-40-201-1007-01 | 2016243 | 1 | MT | ACC | 2018-07-24
PS3MP01-40-201-1007-01 | 2016243 | 4 | MT | ACC | 2018-07-24
PS3MP01-40-201-2005-01 | 2016244 | 7 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2005-01 | 2016244 | 8 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2005-01 | 2016244 | 9 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2005-01 | 2016244 | 10 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2020-01 | 2016250 | 3 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2020-01 | 2016250 | 4 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2003-01 | 2016249 | 1 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2003-01 | 2016249 | 7 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2002-01 | 2016248 | 1 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2002-01 | 2016248 | 7 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-1002-01 | 2016246 | 1 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2001-01 | 2016247 | 1 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-2001-01 | 2016247 | 2 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-1001-01 | 2016245 | 1 | UT/MT | ACC | 2018-07-26
PS3MP01-40-201-1008-02 | 2016231 | 6 | MT | ACC | 2018-07-26
PS3MP01-40-201-2005-02 | 2016232 | 5 | MT | ACC | 2018-07-26
PS3MP01-40-201-2006-02 | 2016233 | 5 | MT | ACC | 2018-07-26
PS3MP01-40-201-2007-02 | 2016234 | 3 | MT | ACC | 2018-07-26
PS3MP01-40-201-2007-02 | 2016234 | 4 | MT | ACC | 2018-07-26
PS3MP01-40-201-2025-02 | 2016235 | 5 | MT | ACC | 2018-07-26
PS3MP01-40-201-2027-02 | 2016236 | 5 | MT | ACC | 2018-07-26
PS3MP01-40-201-2027-02 | 2016236 | 6 | MT | ACC | 2018-07-26
PS3MP01-40-201-3009-02 | 2016237 | 3 | MT | ACC | 2018-07-26
PS3MP01-40-201-3009-02 | 2016237 | 12 | MT | ACC | 2018-07-26
PS3MP01-40-201-3019-02 | 2016238 | 9 | MT | ACC | 2018-07-26
PS3MP01-40-201-3019-02 | 2016238 | 11 | MT | ACC | 2018-07-26
PS3MP01-40-201-2019-01 | 2016251 | 3 | MT | ACC | 2018-07-27
PS3MP01-40-201-2019-01 | 2016251 | 4 | UT/MT | ACC | 2018-07-27
PS3MP01-40-201-2019-01 | 2016251 | 5 | MT | ACC | 2018-07-27
PS3MP01-40-201-2019-01 | 2016251 | 6 | UT/MT | ACC | 2018-07-27
PS3MP01-40-201-2018-01 | 2016253 | 7 | MT | ACC | 2018-07-27
PS3MP01-40-201-2018-01 | 2016253 | 8 | UT/MT | ACC | 2018-07-27
PS3MP01-40-201-2018-01 | 2016253 | 9 | MT | ACC | 2018-07-27
PS3MP01-40-201-2018-01 | 2016253 | 10 | UT/MT | ACC | 2018-07-27
PS3MP01-40-201-2011-01 | 2016252 | 3 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 1 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 2 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 3 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 4 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 5 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 6 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 8 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 9 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 10 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 11 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 12 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 13 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 14 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016254 | 15 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016255 | 10 | MT | ACC | 2018-07-27
PS3MP01-40-201-3001-01 | 2016259 | 1 | MT | ACC | 2018-07-27
PS3MP01-40-201-3001-01 | 2016259 | 5 | MT | ACC | 2018-07-27
PS3MP01-40-201-3001-01 | 2016259 | 9 | UT/MT | ACC | 2018-07-27
PS3MP01-40-201-3001-01 | 2016259 | 13 | MT | ACC | 2018-07-27
PS3MP01-40-201-3004-01 | 2016258 | 2 | MT | ACC | 2018-07-27
PS3MP01-40-201-3004-01 | 2016258 | 4 | MT | ACC | 2018-07-27
PS3MP01-40-201-3004-01 | 2016258 | 6 | MT | ACC | 2018-07-27
PS3MP01-40-201-3004-01 | 2016258 | 8 | UT/MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 1 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 2 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 3 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 4 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 5 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 6 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 7 | MT | ACC | 2018-07-27
PS3MP01-40-201-1009-01 | 2016256 | 8 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016257 | 7 | MT | ACC | 2018-07-27
PS3MP01-40-201-3003-01 | 2016257 | 15 | MT | ACC | 2018-07-28
PS3MP01-40-201-2014-01 | 2016260 | 3 | MT | ACC | 2018-07-28
PS3MP01-40-201-2014-01 | 2016260 | 4 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-2014-01 | 2016260 | 5 | MT | ACC | 2018-07-28
PS3MP01-40-201-2014-01 | 2016260 | 6 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-2013-01 | 2016263 | 5 | MT | ACC | 2018-07-28
PS3MP01-40-201-2013-01 | 2016263 | 6 | MT | ACC | 2018-07-28
PS3MP01-40-201-2013-01 | 2016263 | 11 | MT | ACC | 2018-07-28
PS3MP01-40-201-2013-01 | 2016263 | 12 | MT | ACC | 2018-07-28
PS3MP01-40-201-2012-01 | 2016262 | 1 | MT | ACC | 2018-07-28
PS3MP01-40-201-2012-01 | 2016262 | 2 | MT | ACC | 2018-07-28
PS3MP01-40-201-2012-01 | 2016262 | 3 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-2012-01 | 2016262 | 4 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1010-01 | 2016261 | 2 | MT | ACC | 2018-07-28
PS3MP01-40-201-1010-01 | 2016261 | 4 | MT | ACC | 2018-07-28
PS3MP01-40-201-1010-01 | 2016261 | 6 | MT | ACC | 2018-07-28
PS3MP01-40-201-1010-01 | 2016261 | 8 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 20 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 13 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 14 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 15 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 16 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 17 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 18 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 19 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 5 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 6 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 7 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 8 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 9 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 10 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 11 | MT | ACC | 2018-07-28
PS3MP01-40-201-1008-01 | 2016264 | 12 | MT | ACC | 2018-07-28
PS3MP01-40-201-3004-01 | 2016266 | 1 | MT | ACC | 2018-07-28
PS3MP01-40-201-3004-01 | 2016266 | 3 | MT | ACC | 2018-07-28
PS3MP01-40-201-3004-01 | 2016266 | 5 | MT | ACC | 2018-07-28
PS3MP01-40-201-3004-01 | 2016266 | 7 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-3001-01 | 2016265 | 4 | MT | ACC | 2018-07-28
PS3MP01-40-201-3001-01 | 2016265 | 8 | MT | ACC | 2018-07-28
PS3MP01-40-201-3001-01 | 2016265 | 12 | UT/MT | ACC | 2018-07-28
PS3MP01-40-201-3001-01 | 2016265 | 16 | MT | ACC | 2018-07-28
PS3MP01-40-201-1006-01 | 2016267 | 1 | MT | ACC | 2018-07-28
PS3MP01-40-201-1006-01 | 2016267 | 2 | MT | ACC | 2018-07-28
PS3MP01-40-201-1006-01 | 2016267 | 3 | MT | ACC | 2018-07-28
PS3MP01-40-201-1006-01 | 2016267 | 4 | MT | ACC | 2018-07-28
PS3MP01-40-201-2026-02 | 2016272 | 4 | MT | ACC | 2018-07-30
PS3MP01-40-201-2003-02 | 2016271 | 2 | MT | ACC | 2018-07-30
PS3MP01-40-201-2002-02 | 2016270 | 3 | MT | ACC | 2018-07-30
PS3MP01-40-201-2004-02 | 2016269 | 5 | MT | ACC | 2018-07-30
PS3MP01-40-201-3019-02 | 2016268 | 12 | MT | ACC | 2018-07-30
BHH09A-40-201-2015-02 | 2016276 | 46 | MT | ACC | 2018-07-30
BHH09A-40-201-2019-02 | 2016277 | 27 | MT | ACC | 2018-07-30
BHH09A-40-201-2021-02 | 2016278 | 3 | MT | ACC | 2018-07-30
PS3MP01-40-201-2004-02 | 2016273 | 2 | MT | ACC | 2018-07-30
PS3MP01-40-201-3019-02 | 2016274 | 10 | MT | ACC | 2018-07-30
PS3MP01-40-201-2025-02 | 2016275 | 6 | MT | ACC | 2018-07-30
PS3MP01-40-201-2012-01 | 2016279 | 5 | MT | ACC | 2018-07-31
PS3MP01-40-201-2012-01 | 2016279 | 6 | MT | ACC | 2018-07-31
PS3MP01-40-201-2001-01 | 2016280 | 9 | UT/MT | ACC | 2018-07-31
PS3MP01-40-201-2001-01 | 2016280 | 10 | UT/MT | ACC | 2018-07-31
PS3MP01-40-201-2033-02 | 2016283 | 7 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2033-02 | 2016283 | 8 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2033-02 | 2016283 | 9 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2033-02 | 2016283 | 10 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2033-02 | 2016283 | 11 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2001-02 | 2016281 | 19 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2001-02 | 2016281 | 20 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2001-02 | 2016281 | 21 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2001-02 | 2016281 | 22 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2001-02 | 2016281 | 23 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 17 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 18 | UT/MT | REP | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 19 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 20 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 21 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 22 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 23 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 24 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 25 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2009-02 | 2016282 | 26 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 17 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 18 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 19 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 20 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 21 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 22 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 23 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 24 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 25 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2034-02 | 2016284 | 26 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-1004-01 | 2016285 | 1 | MT | ACC | 2018-08-01
PS3MP01-40-201-1004-01 | 2016285 | 2 | MT | ACC | 2018-08-01
PS3MP01-40-201-2017-01 | 2016287 | 3 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2017-01 | 2016287 | 4 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2017-01 | 2016287 | 6 | MT | ACC | 2018-08-01
PS3MP01-40-201-2017-01 | 2016287 | 7 | MT | ACC | 2018-08-01
PS3MP01-40-201-2023-01 | 2016286 | 3 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2023-01 | 2016286 | 4 | UT/MT | ACC | 2018-08-01
PS3MP01-40-201-2023-01 | 2016286 | 6 | MT | ACC | 2018-08-01
PS3MP01-40-201-2023-01 | 2016286 | 8 | MT | ACC | 2018-08-01
PS3MP01-40-201-1001-02 | 2016288 | 23 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1001-02 | 2016288 | 24 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1001-02 | 2016288 | 25 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1001-02 | 2016288 | 26 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1001-02 | 2016288 | 27 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1002-02 | 2016289 | 23 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1002-02 | 2016289 | 24 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1002-02 | 2016289 | 25 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1002-02 | 2016289 | 26 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1002-02 | 2016289 | 27 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 1 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 2 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 3 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 4 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 5 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 6 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 7 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 8 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 9 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-1029-02 | 2016290 | 10 | UT/MT | ACC | 2018-08-02
PS3MP01-40-201-2006-01 | 2016294 | 1 | MT | ACC | 2018-08-04
PS3MP01-40-201-2006-01 | 2016294 | 2 | MT | ACC | 2018-08-04
PS3MP01-40-201-2006-01 | 2016294 | 25 | UT/MT | REP | 2018-08-04
PS3MP01-40-201-2006-01 | 2016294 | 27 | UT/MT | ACC | 2018-08-04
PS3MP01-40-201-2006-01 | 2016294 | 28 | MT | ACC | 2018-08-04
PS3MP01-40-201-2006-01 | 2016294 | 29 | MT | ACC | 2018-08-04
PS3MP01-40-201-2006-01 | 2016295 | 26 | UT/MT | ACC | 2018-08-04
PS3MP01-40-201-2009-02 | 2016296 | 18R1 | UT/MT | ACC | 2018-08-04
PS3MP01-40-201-3002-01 | 2016291 | 1 | MT | ACC | 2018-08-04
PS3MP01-40-201-3002-01 | 2016291 | 3 | MT | ACC | 2018-08-04
PS3MP01-40-201-3002-01 | 2016291 | 5 | MT | ACC | 2018-08-04
PS3MP01-40-201-3002-01 | 2016291 | 7 | UT/MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 2 | MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 3 | MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 6 | MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 10 | UT/MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 11 | UT/MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 14 | MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016292 | 15 | MT | ACC | 2018-08-04
PS3MP01-40-201-3001-01 | 2016293 | 7 | MT | ACC | 2018-08-04
PS3MP01-40-201-1007-02 | 2016297 | 6 | MT | ACC | 2018-08-04
PS3MP01-40-201-1026-02 | 2016298 | 6 | MT | ACC | 2018-08-04
PS3MP01-40-201-1026-02 | 2016298 | 3 | MT | ACC | 2018-08-04
PS3MP01-40-201-1027-02 | 2016299 | 3 | MT | ACC | 2018-08-04
PS3MP01-40-200-5104-01 | 2016302 | 441 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 442 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 443 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 444 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 445 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 446 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 447 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 448 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 449 | UT/MT | REP | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 450 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 451 | UT/MT | REP | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 452 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 453 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 454 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 455 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 456 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 457 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 458 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 459 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 460 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 466 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 467 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 468 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 469 | UT/MT | ACC | 2018-08-06
PS3MP01-40-200-5104-01 | 2016302 | 470 | UT/MT | ACC | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 1 | MT | ACC | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 2 | MT | ACC | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 39 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 40 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 41 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 42 | MT | ACC | 2018-08-06
PS3MP01-40-201-2007-01 | 2016301 | 43 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 1 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 2 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 3 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 4 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 5 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 6 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 66 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 67 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 68 | MT | ACC | 2018-08-06
PS3MP01-40-201-2005-01 | 2016300 | 69 | UT/MT |  | 2018-08-06
PS3MP01-40-201-2006-01 | 2016303 | 25R1 | UT/MT | ACC | 2018-08-06
PS3MP01-40-201-2002-01 | 2016304 | 2 | MT | ACC | 2018-08-07
PS3MP01-40-201-2002-01 | 2016304 | 4 | MT | ACC | 2018-08-07

## UT OS (hidden)
No | Date Request | NDT DRAWING | LOC | NO.CIR | JOINT | METHOD | THICKNESS | LENGTH | REMARK

## 26 June 18 - 25 July 18
| Total NDT until | 2018-08-07
|  | #REF! | Joint
|  | #REF! | Metres
| NDT Prod / Joint | #REF! | #REF! | #REF! | #REF!
| Date | MT | UT | RT | PT
Week 4 | 2018-07-19 | #REF! | #REF! | #REF! | #REF!
| 2018-07-20 | #REF! | #REF! | #REF! | #REF!
| 2018-07-21 | #REF! | #REF! | #REF! | #REF!
| 2018-07-22 | #REF! | #REF! | #REF! | #REF!
| 2018-07-23 | #REF! | #REF! | #REF! | #REF!
| 2018-07-24 | #REF! | #REF! | #REF! | #REF!
| 2018-07-25 | #REF! | #REF! | #REF! | #REF!
* This period only Structural (Girder's) had been produced by PTMI
* Start Production on 19 July 2018 for QP Bul Hanine Project
|  | MPI CAN's |  |  |  | PT CAN's
|  | #REF! |  | RT Sheets |  | #REF!
| NDT Prod / mm | #REF! | #REF! | #REF! | #REF! | #REF!
| Date | MT | UT | RT (D7 4x10) | RT (D7 4x15) | PT
Week 4 | 2018-07-19 | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-07-20 | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-07-21 | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-07-22 | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-07-23 | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-07-24 | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-07-25 | #REF! | #REF! | #REF! | #REF! | #REF!

## 26 July 18 - 25 Aug 18
|  | Joint | Metres
| Total PT | 0 | 0 |  |  | Total ACC | 312 | [8 empty] | Period | Joint | Metres
| Total RT | 0 | 0 |  |  | Total Rep | 4 | [8 empty] | Jun 18 - Jul 18 | #REF! | #REF!
| Total MT | #REF! | #REF! |  |  | Rej Rate | #REF! | [8 empty] | Jul 18 - Aug 18 | 387 | #REF!
| Total UT | #REF! | #REF!
|  | #REF! | #REF! |  |  |  |  | MPI CAN's |  | PT CAN's
[8 empty] | #REF! |  | #REF! |  |  | RT SHEETS |  | RT JOINT
| NDT Prod / Joint | 256 | 131 | 0 | 0 |  | NDT Prod / mm | #REF! | #REF! | #REF! |  |  | 0 | 0 | #REF!
| Date | MT | UT | RT | PT |  | Date | MT | UT | PT |  | Date | RT (D7 4x10) | RT (D7 4x15)
WEEK 1 | 2018-07-26 | #REF! | #REF! | #REF! | #REF! | WEEK 1 | 2018-07-26 | #REF! | #REF! | #REF! | WEEK 1 | 2018-07-26 |  |  | #REF!
| 2018-07-27 | #REF! | #REF! | #REF! | #REF! |  | 2018-07-27 | #REF! | #REF! | #REF! |  | 2018-07-27 |  |  | #REF!
| 2018-07-28 | #REF! | #REF! | #REF! | #REF! |  | 2018-07-28 | #REF! | #REF! | #REF! |  | 2018-07-28 |  |  | #REF!
| 2018-07-29 | #REF! | #REF! | #REF! | #REF! | Metres | 2018-07-29 | #REF! | #REF! | #REF! |  | 2018-07-29 |  |  | #REF!
| 2018-07-30 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-07-30 | #REF! | #REF! | #REF! |  | 2018-07-30 |  |  | #REF!
| 2018-07-31 | #REF! | #REF! | #REF! | #REF! | Can / W1 | 2018-07-31 | #REF! | #REF! | #REF! |  | 2018-07-31 |  |  | #REF!
| 2018-08-01 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-01 | #REF! | #REF! | #REF! |  | 2018-08-01 |  |  | #REF!
WEEK 2 | 2018-08-02 | #REF! | #REF! | #REF! | #REF! | WEEK 2 | 2018-08-02 | #REF! | #REF! | #REF! | WEEK 2 | 2018-08-02 |  |  | #REF!
| 2018-08-03 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-03 | #REF! | #REF! | #REF! |  | 2018-08-03 |  |  | #REF!
| 2018-08-04 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-04 | #REF! | #REF! | #REF! |  | 2018-08-04 |  |  | #REF!
| 2018-08-05 | #REF! | #REF! | #REF! | #REF! | Metres | 2018-08-05 | #REF! | #REF! | #REF! |  | 2018-08-05 |  |  | #REF!
| 2018-08-06 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-06 | #REF! | #REF! | #REF! |  | 2018-08-06 |  |  | #REF!
| 2018-08-07 | #REF! | #REF! | #REF! | #REF! | Can / W2 | 2018-08-07 | #REF! | #REF! | #REF! |  | 2018-08-07 |  |  | #REF!
| 2018-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-08 | #REF! | #REF! | #REF! |  | 2018-08-08 |  |  | #REF!
WEEK 3 | 2018-08-09 | #REF! | #REF! | #REF! | #REF! | WEEK 3 | 2018-08-09 | #REF! | #REF! | #REF! | WEEK 3 | 2018-08-09 |  |  | #REF!
| 2018-08-10 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-10 | #REF! | #REF! | #REF! |  | 2018-08-10 |  |  | #REF!
| 2018-08-11 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-11 | #REF! | #REF! | #REF! |  | 2018-08-11 |  |  | #REF!
| 2018-08-12 | #REF! | #REF! | #REF! | #REF! | Metres | 2018-08-12 | #REF! | #REF! | #REF! |  | 2018-08-12 |  |  | #REF!
| 2018-08-13 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-13 | #REF! | #REF! | #REF! |  | 2018-08-13 |  |  | #REF!
| 2018-08-14 | #REF! | #REF! | #REF! | #REF! | Can / W3 | 2018-08-14 | #REF! | #REF! | #REF! |  | 2018-08-14 |  |  | #REF!
| 2018-08-15 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-15 | #REF! | #REF! | #REF! |  | 2018-08-15 |  |  | #REF!
WEEK 4 | 2018-08-16 | #REF! | #REF! | #REF! | #REF! | WEEK 4 | 2018-08-16 | #REF! | #REF! | #REF! | WEEK 4 | 2018-08-16 |  |  | #REF!
| 2018-08-17 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-17 | #REF! | #REF! | #REF! |  | 2018-08-17 |  |  | #REF!
| 2018-08-18 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-18 | #REF! | #REF! | #REF! |  | 2018-08-18 |  |  | #REF!
| 2018-08-19 | #REF! | #REF! | #REF! | #REF! | Metres | 2018-08-19 | #REF! | #REF! | #REF! |  | 2018-08-19 |  |  | #REF!
| 2018-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-20 | #REF! | #REF! | #REF! |  | 2018-08-20 |  |  | #REF!
| 2018-08-21 | #REF! | #REF! | #REF! | #REF! | Can / W4 | 2018-08-21 | #REF! | #REF! | #REF! |  | 2018-08-21 |  |  | #REF!
| 2018-08-22 | #REF! | #REF! | #REF! | #REF! | #REF! | 2018-08-22 | #REF! | #REF! | #REF! |  | 2018-08-22 |  |  | #REF!
WEEK 5 | 2018-08-23 | #REF! | #REF! | #REF! | #REF! | WEEK 5 | 2018-08-23 | #REF! | #REF! | #REF! | WEEK 5 | 2018-08-23 |  |  | #REF!
| 2018-08-24 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-24 | #REF! | #REF! | #REF! |  | 2018-08-24 |  |  | #REF!
| 2018-08-25 | #REF! | #REF! | #REF! | #REF! |  | 2018-08-25 | #REF! | #REF! | #REF! |  | 2018-08-25 |  |  | #REF!